## Sheet1
| Overview of current NAFLD Experiments | [15 empty] | Lab |  |  | Wildlings
|  |  |  | Diets | [12 empty] | Mice on CD | Mice on HFD | Total Lab | Mice on CD | Mice on HFD | total Wildlings | All mice
| Start Date | 10 Week Date | 20 Week Date | CD Lab | HFD Lab | CD Wildlings | HFD Wildlings | Microbiome | Sex | Birthdate From | To | Age at Start averaged for wildlings | Shipment Received | Origin | Purpose | Comments | 124 | 178 | 302 | 54 | 101 | 155 | 457
E1 | 2018-06-19 | 2018-08-28 | 2018-11-06 |  |  | 10 | 20 | Wildling | F | 2018-03-28 | 2018-04-05 | 11.2857 |  | F22 |  | F22
| 2018-06-19 | 2018-08-28 | 2018-11-06 | 12 | 15 |  |  | Lab | F | 2018-04-09 |  | 10.1429 | 2018-06-07 | Taconic
E2 | 2018-07-11 | 2018-09-19 | 2018-11-28 | 15 | 20 |  |  | Lab | F | 2018-05-04 |  | 9.7143 | 2018-07-06 | Taconic
| 2018-07-12 | 2018-09-20 | 2018-11-29 |  |  | 10 | 20 | Wildling | F | 2018-04-28 | 2018-05-12 | 9.7143 |  | F24 |  | F24
Metabolon | 2018-07-12 | 2018-09-20 | 2018-11-29 |  |  |  | 5 | Wildling | F | [5 empty] | Metabolon | only 5 wildings were left to use, all put on HFD
MALE | 2018-07-23 | 2018-10-01 | 2018-12-10 |  |  | 5 | 5 | Wildling | M |  |  | 6186.2857 |  |  |  | killed due to fighting
MALE | 2018-07-25 | 2018-10-03 | 2018-12-12 | 5 | 5 |  |  | Lab | M |  |  |  |  | Taconic |  | killed due to fighting
E3 | 2018-08-08 | 2018-10-17 | 2018-12-26 | 15 | 20 |  |  | Lab | F | 2018-05-21 |  | 11.2857 | 2018-07-26
| 2018-08-09 | 2018-10-18 | 2018-12-27 |  |  | 10 | 20 | Wildling | F | 2018-05-29 | 2018-06-17 | 8.9286 |  | F26/27
Metabolon | 2018-07-23 | 2018-10-01 | 2018-12-10 |  |  | 10 | 15 | Wildling | F | 2018-04-12 | 2018-04-23 | 14.5714 |  | F23 | Metabolon | F23
Metabolon | 2018-08-24 | 2018-11-02 | 2019-01-11 | 15 | 15 |  |  |  | F | 2018-06-11 |  | 10.5714 | 2018-08-09 | Taconic | Metabolon
M1 Lab | 2018-08-24 | 2018-11-02 | 2019-01-11 | 7 | 8 |  |  |  | M | 2018-06-11 |  | 10.5714 | 2018-08-09 | Taconic |  | 5 mice in 14C were fighting and had to be euthanized prior to start of Experiment
F | 2018-08-30 | 2018-11-08 | 2019-01-17 | 20 | 20 |  |  |  | F | 2018-06-18 |  | 10.4286 | 2018-08-14 | Taconic | Metabolon | CC00665599 - CC00665606
M1 Wild | 2018-09-06 | 2018-11-15 | 2019-01-24 | 7 | 8 |  |  |  | M | 2018-06-20 | 2018-07-01 | 10.3571 |  | M28
Female | 2018-08-30 | 2018-11-08 | 2019-01-17 | 20 | 20 |  |  |  | F | 2018-06-20 |  | 10.1429 | 2018-08-16 | Taconic | Metabolon | CC00665304 - CC00665297
Female | 2018-11-16 | 2019-01-25 | 2019-04-05 |  | 10 |  |  | Lab | F | 2018-09-03 | 2018-09-03 | 10.5714 |  | Taconic | Metabolon
M 2 Lab | 2018-11-23 | 2019-02-01 | 2019-04-12 | 8 | 12 |  |  | Lab | M | 2018-09-03 | 2018-09-03 | 11.5714 | 2018-10-30 | Taconic | Experiment Male
Female | 2018-12-05 | 2019-02-13 | 2019-04-24 | 10 | 25 |  |  | Lab | F | 2018-09-24 | 2018-09-24 | 10.2857 | 2018-11-20 | Taconic | Female
Female | 2018-12-12 | 2019-02-20 | 2019-05-01 |  |  | 9 | 16 | Wildling | F |  |  |  |  | F33 | Female | Initial seperation for fecal bomb calorimetry

## Experimental Planning
| Overview of current NAFLD Experiments | [31 empty] | Lab |  |  | Wildlings
|  |  |  | Diets | [28 empty] | Mice on CD | Mice on HFD | Total Lab | Mice on CD | Mice on HFD | total Wildlings | All mice
| Start Date | 10 Week Date | 20 Week Date | CD Lab | HFD Lab | CD Wildlings | HFD Wildlings | Microbiome | Sex | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | Birthdate From | To | Age at Start averaged for wildlings | Shipment Received | Origin | Purpose | Comments | 124 | 218 | 342 | 64 | 121 | 185 | 527
E1 | 2018-06-19 | 2018-08-28 | 2018-11-06 |  |  | 10 | 20 | Wildling | F | [16 empty] | 2018-03-28 | 2018-04-05 | 11.2857 |  | F22 |  | F22
| 2018-06-19 | 2018-08-28 | 2018-11-06 | 12 | 15 |  |  | Lab | F | [16 empty] | 2018-04-09 |  | 10.1429 | 2018-06-07 | Taconic
E2 | 2018-07-11 | 2018-09-19 | 2018-11-28 | 15 | 20 |  |  | Lab | F | [16 empty] | 2018-05-04 |  | 9.7143 | 2018-07-06 | Taconic
| 2018-07-12 | 2018-09-20 | 2018-11-29 |  |  | 10 | 20 | Wildling | F | [16 empty] | 2018-04-28 | 2018-05-12 | 9.7143 |  | F24 |  | F24
Metabolon | 2018-07-12 | 2018-09-20 | 2018-11-29 |  |  |  | 5 | Wildling | F | [21 empty] | Metabolon | only 5 wildings were left to use, all put on HFD
MALE | 2018-07-23 | 2018-10-01 | 2018-12-10 |  |  | 5 | 5 | Wildling | M | [18 empty] | 6186.2857 |  |  |  | killed due to fighting
MALE | 2018-07-25 | 2018-10-03 | 2018-12-12 | 5 | 5 |  |  | Lab | M | [20 empty] | Taconic |  | killed due to fighting
E3 | 2018-08-08 | 2018-10-17 | 2018-12-26 | 15 | 20 |  |  | Lab | F | [16 empty] | 2018-05-21 |  | 11.2857 | 2018-07-26
| 2018-08-09 | 2018-10-18 | 2018-12-27 |  |  | 10 | 20 | Wildling | F | [16 empty] | 2018-05-29 | 2018-06-17 | 8.9286 |  | F26/27
Metabolon | 2018-07-23 | 2018-10-01 | 2018-12-10 |  |  | 10 | 15 | Wildling | F | [16 empty] | 2018-04-12 | 2018-04-23 | 14.5714 |  | F23 | Metabolon | F23
Metabolon | 2018-08-24 | 2018-11-02 | 2019-01-11 | 15 | 15 |  |  |  | F | 2019-01-01: Glucose and Insulin Testing Week 20 Chow and HFD | 2018-06-11 |  | 10.5714 | 2018-08-09 | Taconic | Metabolon
M1 Lab | 2018-08-24 | 2018-11-02 | 2019-01-11 | 7 | 8 |  |  |  | M | 2019-01-01: Basic Readout Male E1 Lab (eg Liver histology etc) | 2018-06-11 |  | 10.5714 | 2018-08-09 | Taconic |  | 5 mice in 14C were fighting and had to be euthanized prior to start of Experiment
F | 2018-08-30 | 2018-11-08 | 2019-01-17 | 20 | 20 |  |  |  | F | 2019-01-01: Last Week of January: Glucose Week 20 | 2018-06-18 |  | 10.4286 | 2018-08-14 | Taconic | Metabolon | CC00665599 - CC00665606
M1 Wild | 2018-09-06 | 2018-11-15 | 2019-01-24 | 7 | 8 |  |  |  | M | [16 empty] | 2018-06-20 | 2018-07-01 | 10.3571 |  | M28
Female | 2018-08-30 | 2018-11-08 | 2019-01-17 | 20 | 20 |  |  |  | F | 2019-01-01: MR Body Composition Week 20 Lab; 2019-02-01: Week 20 Lab Harvest for Metabolon | 2018-06-20 |  | 10.1429 | 2018-08-16 | Taconic | Metabolon | CC00665304 - CC00665297
Female | 2018-11-16 | 2019-01-25 | 2019-04-05 |  | 10 |  |  | Lab | F | 2019-02-01: LPS Challenge | 2018-09-03 | 2018-09-03 | 10.5714 |  | Taconic | Metabolon
M 2 Lab | 2018-11-23 | 2019-02-01 | 2019-04-12 | 8 | 12 |  |  | Lab | M | 2019-02-01: LPS Challenge And Bounce Back; 2019-04-01: E2 Male Harvest W 20 | 2018-09-03 | 2018-09-03 | 11.5714 | 2018-10-30 | Taconic | Experiment Male
Female | 2018-12-05 | 2019-02-13 | 2019-04-24 | 10 | 25 |  |  | Lab | F | 2019-02-01: MR Body Composition Week 10; 2019-04-01: MR Body Composition Week 20 | 2018-09-24 | 2018-09-24 | 10.2857 | 2018-11-20 | Taconic | Female
Female | 2018-12-12 | 2019-02-20 | 2019-05-01 |  |  | 9 | 16 | Wildling | F | 2019-01-01: Week 5 for running wheels; 2019-02-01: 2/6/2019: Week 8 of HFD: 3rd time point for fecal bomb calorimetry; 2019-03-01: Week 10 for runnig wheels, LPS Challenge; 2019-04-01: Body Composition Week 20, Glucose and Insulin Challenge; 2019-05-01: Harvest W 20 |  |  |  |  | F33 | Female | Initial seperation for fecal bomb calorimetry
Female | 2019-01-20 | 2019-03-31 | 2019-06-09 | 15 | 20 |  |  | Lab | F | 2019-01-01: Fecal Harvest Lab E 1, Baseline; 2019-02-01: Fecal Harvest Lab E 1 Timpoint 2; 2019-03-01: 3/17/2019: Fecal Harvest Week 8 E 1 Lab
Female | 2019-02-02 | 2019-04-13 | 2019-06-22 | 15 | 20 |  |  |  |  | 2019-02-01: Fecal Harvest Lab E 2, Baseline and Timepoint 1; 2019-03-01: 3/30/2019: Fecal Harvest Week 8 E2 Lab
Female | 2019-02-06 | 2019-04-17 | 2019-06-26 |  |  | 10 | 20 | Wildling | F | 2019-02-01: Fecal Harvest Wild E2, Baseline; 2019-03-01: Fecal Harvest E2 Wild, Timepoint 1; 2019-04-01: 4/3/19: Timepoint 2, Week 8, Wild E2 fecal collection; 2019-06-01: Harvest W 20
Week 5 Running Wheels
General Experiments, not limited to a certain mouse group | [9 empty] | 2019-01-01: Prepare Sequencing of Gut Content!!!; 2019-03-01: Analysis for Sequencing and preparation of additional experiments; 2019-04-01: Inoculate mice with predefined set of microbes that might be likely to cause weight loss phenotyp
Practice RNA Extraction